## Task List
(Project ) Task List & Estimated Resources
Task |  |  |  |  | P.Period
Phase | Lv1 | Lv2 | Lv3 | Lv4
Ⅰ. Migration for on-premise ODS to Cloud ODS
1. Migration for on-premise (PROD#09) ODS to Cloud(AWS) ODS
1-1. Determining the scope of migration within the (PROD) DB
1-1-1. Selection for Target Schema
1-1-1-1. Target list selection by interface check with application
1-1-1-2. Target list selection by business logic
1-1-1-3. Target list cross check by existed DW for BI
1-1-1-4. Target list cross check by existed SSRS Report
1-1-2. Selection for Target Table & View
1-1-2-1. Target list selection by interface check with application
1-1-2-2. Target list selection by business logic
1-1-2-3. Target list cross check by existed DW for BI
1-1-2-4. Target list cross check by existed SSRS Report
1-1-3. Selection for DB Index
1-1-3-1. Target list selection by interface check with application
1-1-3-2. Target list selection by business logic
1-1-3-3. Target list cross check by existed DW for BI
1-1-3-4. Target list cross check by existed SSRS Report
1-1-4. Selection fot Target DB Access Role
1-1-4-1. Target list selection by interface check with application
1-1-4-2. Target list selection by business logic
1-1-4-3. Target list cross check by existed DW for BI
1-1-4-4. Target list cross check by existed SSRS Report
1-2. To run a backup of (PROD) ODS Server
1-2-1. To run a backup of (PROD) SQL Database
1-2-2. To run a backup of (PROD) SQL Server Integration Service
1-2-3. To run a backup of (PROD) SQL Server Analysis Service
1-2-4. To run a Backup of (PROD) SQL Server Reporting Service
1-3. Installing ODS Server in the Cloud (AWS)
1-3-1. Check hardware and software requirements.
1-3-2. Download the installation file
1-3-3. Run the installation wizard
1-4. Modifying the interface logic of applications for the ODS server
1-5. Restoring DB on a new ODS Server
1-5-1. Restoring Database on Cloud Server
1-5-2. Execute Database upgrade
1-6. Server Migration Final check
1-6-1. Check if the database is functioning properly on the cloud ODS server
1-6-2. Check the interface of the application associated with the cloud ODS server
1-7. Server Replication and Interface Check
1-7-1. DB Backup and (New)DEV Server DB Restore
1-7-2. DB Backup and (New)QAS Server DB Restore
1-7-3. Check the interface of the application associated with the cloud (DEV) ODS server
1-7-4. Check the interface of the application associated with the cloud (QAS) ODS server
1-8. Operations and Hypercare
2. Migration for on-premise (PROD#10) ODS to Cloud(AWS) ODS
2-1. Determining the scope of migration within the (PROD) DB
2-1-1. Selection for Target Schema
2-1-1-1. Target list selection by interface check with application
2-1-1-2. Target list selection by business logic
2-1-1-3. Target list cross check by existed DW for BI
2-1-1-4. Target list cross check by existed SSRS Report
2-1-2. Selection for Target Table & View
2-1-2-1. Target list selection by interface check with application
2-1-2-2. Target list selection by business logic
2-1-2-3. Target list cross check by existed DW for BI
2-1-2-4. Target list cross check by existed SSRS Report
2-1-3. Selection for DB Index
2-1-3-1. Target list selection by interface check with application
2-1-3-2. Target list selection by business logic
2-1-3-3. Target list cross check by existed DW for BI
2-1-3-4. Target list cross check by existed SSRS Report
2-1-4. Selection fot Target DB Access Role
2-1-4-1. Target list selection by interface check with application
2-1-4-2. Target list selection by business logic
2-1-4-3. Target list cross check by existed DW for BI
2-1-4-4. Target list cross check by existed SSRS Report
2-2. To run a backup of (PROD) ODS Server
2-2-1. To run a backup of (PROD) SQL Database
2-2-2. To run a backup of (PROD) SQL Server Integration Service
2-2-3. To run a backup of (PROD) SQL Server Analysis Service
2-2-4. To run a Backup of (PROD) SQL Server Reporting Service
2-3. Installing ODS Server in the Cloud (AWS)
2-3-1. Check hardware and software requirements.
2-3-2. Download the installation file
2-3-3. Run the installation wizard
2-4. Modifying the interface logic of applications for the ODS server
2-5. Restoring DB on a new ODS Server
2-5-1. Restoring Database on Cloud Server
2-5-2. Execute Database upgrade
2-6. Server Migration Final check
2-6-1. Check if the database is functioning properly on the cloud ODS server
2-6-2. Check the interface of the application associated with the cloud ODS server
2-7. Server Replication and Interface Check
2-7-1. DB Backup and (New)DEV Server DB Restore
2-7-2. DB Backup and (New)QAS Server DB Restore
2-7-3. Check the interface of the application associated with the cloud (DEV) ODS server
2-7-4. Check the interface of the application associated with the cloud (QAS) ODS server
2-8. Operations and Hypercare
Ⅱ. CORIA Project Enhancement
1. Data Warehouse Modification Development
1-1. SQL Server Integration Service Enhancement Task
1-1-1. List up detailed content of source data
1-1-2. Change for Source Data of Connection
1-1-3. Package Debug and modifiying Development
1-1-4. Deploying SSIS Packages on a Server
1-1-5. Package scheduling and monitoring
1-2. Add New Attribute on existed Data Warehouse
1-2-1. Modification development of existing package
1-2-2. Checking the impact of Dimension Table changes
1-2-3. Checking the impact of Fact Table changes
1-2-4. Package Debug and modifiying Development
1-2-5. Deploying SSIS Packages on a Server
1-2-6. Package scheduling and monitoring
2. Data Mart (OLAP) Modification Development
2-1. SQL Server Analysis Service Enhancement Task
2-1-1. List up detailed content of source data
2-1-2. Package Debug and modifiying development
2-1-3. Deploying SSAS Packages on a Server (Processing)
2-1-4. Package scheduling and monitoring
2-2. Add New Attribute on existed Data Mart (OLAP)
2-2-1. Data Table Processing
2-2-2. Create measure or modify measure
2-2-3. Deploying SSAS Packages on a Server (Processing)
2-2-4. Package scheduling and monitoring
2-3. OLAP Data Incremental processing & partitioning
2-3-1. Modification development of Incremental processing
2-3-2. Modification development of data partitioning
2-3-3. Package Debug and modifiying development
2-3-4. Deploying SSAS Packages on a Server (Processing)
2-3-5. Package scheduling and monitoring
2-4. OLAP Model Configuration management
2-4-1. Git Repository 생성
2-4-2. SSAS connect to Git repository
Ⅲ. Convert SQL Server Reporting Server to Power BI
1. Convert SQL Server Reporting Server to Power BI
1-1. Screen Layout Design
1-1-1. Receive "Power bi Development Request (Doc)"
1-1-2. Design "Screen Layout Format"
1-1-3. Design "Power BI Storyboard"
1-2. Add new data on existed Data Warehouse
1-2-1. List up detailed content of source data
1-2-2. Modification development of existing package
1-2-3. Checking the impact of Dimension Table changes
1-2-4. Checking the impact of Fact Table changes
1-2-5. Package Debug and modifiying Development
1-2-6. Deploying SSIS Packages on a Server
1-2-7. Package scheduling and monitoring
1-3. Create new Data Mart (OLAP)
1-3-1. Data Table Processing
1-3-2. Set table relation
1-3-3. Create measure or modify measure
1-3-4. Deploying SSAS Packages on a Server (Processing)
1-3-5. Package scheduling and monitoring
1-4. Visualize on Power BI
1-4-1. Set details of visualized objects
1-4-2. Modify measures in need
1-4-3. Go through UAT(User Acceptance Test)
1-4-4. Operations and Hypercare